## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Phần mềm quản lý với 3 module chính: Quản lý thu phí, Quản lý người dùng, Quản lý hộ gia đình
| Xây dựng phần mềm quản lý và thu phí ở chung cư Blue Moon | Hà Trung Chiến | 2023-10-02 | 2023-12-30 |  | 0% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Hà Trung Chiến |  | 2023-10-02 | 2023-10-13 | 10 | Not Started
| User login and authentication | User Management | Nguyễn Bùi Tuấn Linh | 5 | 2023-10-02 | 2023-10-06 | 5 | Not Started
| User role and permission management | User Management | Phạm Quốc Cường | 8 | 2023-10-04 | 2023-10-10 | 7 | Not Started
| Add/Edit household information | Household Management | Hồ Tuấn Huy | 5 | 2023-10-02 | 2023-10-05 | 4 | Not Started
| View household and resident details | Household Management | Phạm Quốc Cường | 3 | 2023-10-05 | 2023-10-07 | 3 | Not Started
| Sprint 2 |  | Hà Trung Chiến |  | 2023-10-16 | 2023-10-27 | 10 | Not Started
| User profile management | User Management | Nguyễn Khánh Toàn | 3 | 2023-10-16 | 2023-10-18 | 3 | Not Started
| Add/Edit resident information | Household Management | Nguyễn Bùi Tuấn Linh | 5 | 2023-10-16 | 2023-10-20 | 5 | Not Started
| Define fee types | Fee Management | Nguyễn Khánh Toàn | 3 | 2023-10-18 | 2023-10-22 | 5 | Not Started
| Record fee payments | Fee Management | Hồ Tuấn Huy | 8 | 2023-10-20 | 2023-10-25 | 6 | Not Started
| Sprint 3 |  | Hà Trung Chiến |  | 2023-10-30 | 2023-11-10 | 10 | Not Started
| Generate fee reports | Fee Management | Nguyễn Bùi Tuấn Linh | 5 | 2023-10-30 | 2023-11-03 | 5 | Not Started
| Integrate all modules | Integration | Phạm Quốc Cường | 8 | 2023-11-01 | 2023-11-07 | 7 | Not Started
| UI enhancements | UI/UX | Nguyễn Khánh Toàn | 5 | 2023-11-03 | 2023-11-08 | 6 | Not Started
| Testing and bug fixes | Quality Assurance | Hồ Tuấn Huy | 13 | 2023-11-05 | 2023-11-10 | 6 | Not Started